## Sheet1
Date | Week | Day | Task Category | Task Description | Status (✅/❌) | Notes | Learning Resource Link
2025-06-17 | Week 1 | Day 1 | .NET + C# Task | Install .NET SDK & VS Code | ✅ |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-17 | Week 1 | Day 1 | Angular Task | Install Node, Angular CLI | ✅ |  | https://angular.io/start
2025-06-17 | Week 1 | Day 1 | Azure Task | Create Azure Free Account | ✅ |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-17 | Week 1 | Day 1 | Project Module | Define project scope and modules | ✅ |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-17 | Week 1 | Day 1 | Communication Practice | Record: Who am I and why this project? |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-17 | Week 1 | Day 1 | Reflection/Notes | What did I struggle with? |  |  | https://www.notion.so/personal-reflection-template
2025-06-18 | Week 1 | Day 2 | .NET + C# Task | Understand C# syntax & data types |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-18 | Week 1 | Day 2 | Angular Task | Create Angular app + understand structure |  |  | https://angular.io/start
2025-06-18 | Week 1 | Day 2 | Azure Task | Explore Azure Portal & Resource Groups |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-18 | Week 1 | Day 2 | Project Module | Setup GitHub Repo + readme |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-18 | Week 1 | Day 2 | Communication Practice | Explain what OOP is in C# |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-18 | Week 1 | Day 2 | Reflection/Notes | What clicked for me today? |  |  | https://www.notion.so/personal-reflection-template
2025-06-19 | Week 1 | Day 3 | .NET + C# Task | Practice OOP: Class, Object, Inheritance |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-19 | Week 1 | Day 3 | Angular Task | Components and Modules |  |  | https://angular.io/start
2025-06-19 | Week 1 | Day 3 | Azure Task | Understand App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-19 | Week 1 | Day 3 | Project Module | Design database schema |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-19 | Week 1 | Day 3 | Communication Practice | Explain Angular component to yourself |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-19 | Week 1 | Day 3 | Reflection/Notes | Any blocker faced in setup? |  |  | https://www.notion.so/personal-reflection-template
2025-06-20 | Week 1 | Day 4 | .NET + C# Task | Create first Console App |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-20 | Week 1 | Day 4 | Angular Task | Data binding & directives |  |  | https://angular.io/start
2025-06-20 | Week 1 | Day 4 | Azure Task | Deploy sample HTML to App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-20 | Week 1 | Day 4 | Project Module | Create login API |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-20 | Week 1 | Day 4 | Communication Practice | Describe Azure in 1 min voice note |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-20 | Week 1 | Day 4 | Reflection/Notes | Comfort level with code so far |  |  | https://www.notion.so/personal-reflection-template
2025-06-21 | Week 1 | Day 5 | .NET + C# Task | Intro to API: Build simple REST API |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-21 | Week 1 | Day 5 | Angular Task | Routing basics |  |  | https://angular.io/start
2025-06-21 | Week 1 | Day 5 | Azure Task | Install Azure CLI |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-21 | Week 1 | Day 5 | Project Module | Create Angular login UI |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-21 | Week 1 | Day 5 | Communication Practice | Mock intro: job interview |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-21 | Week 1 | Day 5 | Reflection/Notes | How did I feel explaining in English? |  |  | https://www.notion.so/personal-reflection-template
2025-06-22 | Week 1 | Day 6 | .NET + C# Task | Entity Framework Core basics |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-22 | Week 1 | Day 6 | Angular Task | Create Login form (HTML + CSS) |  |  | https://angular.io/start
2025-06-22 | Week 1 | Day 6 | Azure Task | Learn Azure SQL Basics |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-22 | Week 1 | Day 6 | Project Module | Bind login API to UI |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-22 | Week 1 | Day 6 | Communication Practice | Talk about your project idea |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-22 | Week 1 | Day 6 | Reflection/Notes | What would I improve? |  |  | https://www.notion.so/personal-reflection-template
2025-06-23 | Week 1 | Day 7 | .NET + C# Task | Integrate DB with API (SQL Server) |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-23 | Week 1 | Day 7 | Angular Task | Service and API call integration |  |  | https://angular.io/start
2025-06-23 | Week 1 | Day 7 | Azure Task | Create Azure SQL DB |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-23 | Week 1 | Day 7 | Project Module | Test end-to-end login flow |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-23 | Week 1 | Day 7 | Communication Practice | Weekly recap in voice |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-23 | Week 1 | Day 7 | Reflection/Notes | Week 1 wins & learnings |  |  | https://www.notion.so/personal-reflection-template
2025-06-24 | Week 2 | Day 1 | .NET + C# Task | Install .NET SDK & VS Code |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-24 | Week 2 | Day 1 | Angular Task | Install Node, Angular CLI |  |  | https://angular.io/start
2025-06-24 | Week 2 | Day 1 | Azure Task | Enhance Azure Free Account |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-24 | Week 2 | Day 1 | Project Module | Define project scope and modules |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-24 | Week 2 | Day 1 | Communication Practice | Record: Who am I and why this project? |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-24 | Week 2 | Day 1 | Reflection/Notes | What did I struggle with? |  |  | https://www.notion.so/personal-reflection-template
2025-06-25 | Week 2 | Day 2 | .NET + C# Task | Deep dive into C# syntax & data types |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-25 | Week 2 | Day 2 | Angular Task | Enhance Angular app + understand structure |  |  | https://angular.io/start
2025-06-25 | Week 2 | Day 2 | Azure Task | Explore Azure Portal & Resource Groups |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-25 | Week 2 | Day 2 | Project Module | Setup GitHub Repo + readme |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-25 | Week 2 | Day 2 | Communication Practice | Explain what OOP is in C# |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-25 | Week 2 | Day 2 | Reflection/Notes | What clicked for me today? |  |  | https://www.notion.so/personal-reflection-template
2025-06-26 | Week 2 | Day 3 | .NET + C# Task | Practice OOP: Class, Object, Inheritance with real-world scenario |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-26 | Week 2 | Day 3 | Angular Task | Components and Modules |  |  | https://angular.io/start
2025-06-26 | Week 2 | Day 3 | Azure Task | Deep dive into App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-26 | Week 2 | Day 3 | Project Module | Design database schema |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-26 | Week 2 | Day 3 | Communication Practice | Explain Angular component to yourself |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-26 | Week 2 | Day 3 | Reflection/Notes | Any blocker faced in setup? |  |  | https://www.notion.so/personal-reflection-template
2025-06-27 | Week 2 | Day 4 | .NET + C# Task | Enhance first Console App |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-27 | Week 2 | Day 4 | Angular Task | Data binding & directives |  |  | https://angular.io/start
2025-06-27 | Week 2 | Day 4 | Azure Task | Deploy sample HTML to App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-27 | Week 2 | Day 4 | Project Module | Enhance login API + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-27 | Week 2 | Day 4 | Communication Practice | Describe Azure in 1 min voice note |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-27 | Week 2 | Day 4 | Reflection/Notes | Comfort level with code so far |  |  | https://www.notion.so/personal-reflection-template
2025-06-28 | Week 2 | Day 5 | .NET + C# Task | Advanced to API: Build simple REST API + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-28 | Week 2 | Day 5 | Angular Task | Routing basics |  |  | https://angular.io/start
2025-06-28 | Week 2 | Day 5 | Azure Task | Install Azure CLI |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-28 | Week 2 | Day 5 | Project Module | Enhance Angular login UI |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-28 | Week 2 | Day 5 | Communication Practice | Mock intro: job interview |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-28 | Week 2 | Day 5 | Reflection/Notes | How did I feel explaining in English? |  |  | https://www.notion.so/personal-reflection-template
2025-06-29 | Week 2 | Day 6 | .NET + C# Task | Entity Framework Core basics |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-29 | Week 2 | Day 6 | Angular Task | Enhance Login form (HTML + CSS) |  |  | https://angular.io/start
2025-06-29 | Week 2 | Day 6 | Azure Task | Learn Azure SQL Basics |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-29 | Week 2 | Day 6 | Project Module | Bind login API to UI + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-29 | Week 2 | Day 6 | Communication Practice | Talk about your project idea |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-29 | Week 2 | Day 6 | Reflection/Notes | What would I improve? |  |  | https://www.notion.so/personal-reflection-template
2025-06-30 | Week 2 | Day 7 | .NET + C# Task | Integrate DB with API (SQL Server) + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-06-30 | Week 2 | Day 7 | Angular Task | Service and API call integration + validation |  |  | https://angular.io/start
2025-06-30 | Week 2 | Day 7 | Azure Task | Enhance Azure SQL DB |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-06-30 | Week 2 | Day 7 | Project Module | Test end-to-end login flow |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-06-30 | Week 2 | Day 7 | Communication Practice | Weekly recap in voice |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-06-30 | Week 2 | Day 7 | Reflection/Notes | Week 1 wins & learnings |  |  | https://www.notion.so/personal-reflection-template
2025-07-01 | Week 3 | Day 1 | .NET + C# Task | Install .NET SDK & VS Code |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-01 | Week 3 | Day 1 | Angular Task | Install Node, Angular CLI |  |  | https://angular.io/start
2025-07-01 | Week 3 | Day 1 | Azure Task | Enhance Azure Free Account |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-01 | Week 3 | Day 1 | Project Module | Define project scope and modules |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-01 | Week 3 | Day 1 | Communication Practice | Record: Who am I and why this project? |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-01 | Week 3 | Day 1 | Reflection/Notes | What did I struggle with? |  |  | https://www.notion.so/personal-reflection-template
2025-07-02 | Week 3 | Day 2 | .NET + C# Task | Deep dive into C# syntax & data types |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-02 | Week 3 | Day 2 | Angular Task | Enhance Angular app + understand structure |  |  | https://angular.io/start
2025-07-02 | Week 3 | Day 2 | Azure Task | Explore Azure Portal & Resource Groups |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-02 | Week 3 | Day 2 | Project Module | Setup GitHub Repo + readme |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-02 | Week 3 | Day 2 | Communication Practice | Explain what OOP is in C# |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-02 | Week 3 | Day 2 | Reflection/Notes | What clicked for me today? |  |  | https://www.notion.so/personal-reflection-template
2025-07-03 | Week 3 | Day 3 | .NET + C# Task | Practice OOP: Class, Object, Inheritance with real-world scenario |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-03 | Week 3 | Day 3 | Angular Task | Components and Modules |  |  | https://angular.io/start
2025-07-03 | Week 3 | Day 3 | Azure Task | Deep dive into App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-03 | Week 3 | Day 3 | Project Module | Design database schema |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-03 | Week 3 | Day 3 | Communication Practice | Explain Angular component to yourself |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-03 | Week 3 | Day 3 | Reflection/Notes | Any blocker faced in setup? |  |  | https://www.notion.so/personal-reflection-template
2025-07-04 | Week 3 | Day 4 | .NET + C# Task | Enhance first Console App |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-04 | Week 3 | Day 4 | Angular Task | Data binding & directives |  |  | https://angular.io/start
2025-07-04 | Week 3 | Day 4 | Azure Task | Deploy sample HTML to App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-04 | Week 3 | Day 4 | Project Module | Enhance login API + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-04 | Week 3 | Day 4 | Communication Practice | Describe Azure in 1 min voice note |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-04 | Week 3 | Day 4 | Reflection/Notes | Comfort level with code so far |  |  | https://www.notion.so/personal-reflection-template
2025-07-05 | Week 3 | Day 5 | .NET + C# Task | Advanced to API: Build simple REST API + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-05 | Week 3 | Day 5 | Angular Task | Routing basics |  |  | https://angular.io/start
2025-07-05 | Week 3 | Day 5 | Azure Task | Install Azure CLI |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-05 | Week 3 | Day 5 | Project Module | Enhance Angular login UI |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-05 | Week 3 | Day 5 | Communication Practice | Mock intro: job interview |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-05 | Week 3 | Day 5 | Reflection/Notes | How did I feel explaining in English? |  |  | https://www.notion.so/personal-reflection-template
2025-07-06 | Week 3 | Day 6 | .NET + C# Task | Entity Framework Core basics |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-06 | Week 3 | Day 6 | Angular Task | Enhance Login form (HTML + CSS) |  |  | https://angular.io/start
2025-07-06 | Week 3 | Day 6 | Azure Task | Learn Azure SQL Basics |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-06 | Week 3 | Day 6 | Project Module | Bind login API to UI + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-06 | Week 3 | Day 6 | Communication Practice | Talk about your project idea |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-06 | Week 3 | Day 6 | Reflection/Notes | What would I improve? |  |  | https://www.notion.so/personal-reflection-template
2025-07-07 | Week 3 | Day 7 | .NET + C# Task | Integrate DB with API (SQL Server) + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-07 | Week 3 | Day 7 | Angular Task | Service and API call integration + validation |  |  | https://angular.io/start
2025-07-07 | Week 3 | Day 7 | Azure Task | Enhance Azure SQL DB |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-07 | Week 3 | Day 7 | Project Module | Test end-to-end login flow |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-07 | Week 3 | Day 7 | Communication Practice | Weekly recap in voice |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-07 | Week 3 | Day 7 | Reflection/Notes | Week 1 wins & learnings |  |  | https://www.notion.so/personal-reflection-template
2025-07-08 | Week 4 | Day 1 | .NET + C# Task | Install .NET SDK & VS Code |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-08 | Week 4 | Day 1 | Angular Task | Install Node, Angular CLI |  |  | https://angular.io/start
2025-07-08 | Week 4 | Day 1 | Azure Task | Enhance Azure Free Account |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-08 | Week 4 | Day 1 | Project Module | Define project scope and modules |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-08 | Week 4 | Day 1 | Communication Practice | Record: Who am I and why this project? |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-08 | Week 4 | Day 1 | Reflection/Notes | What did I struggle with? |  |  | https://www.notion.so/personal-reflection-template
2025-07-09 | Week 4 | Day 2 | .NET + C# Task | Deep dive into C# syntax & data types |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-09 | Week 4 | Day 2 | Angular Task | Enhance Angular app + understand structure |  |  | https://angular.io/start
2025-07-09 | Week 4 | Day 2 | Azure Task | Explore Azure Portal & Resource Groups |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-09 | Week 4 | Day 2 | Project Module | Setup GitHub Repo + readme |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-09 | Week 4 | Day 2 | Communication Practice | Explain what OOP is in C# |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-09 | Week 4 | Day 2 | Reflection/Notes | What clicked for me today? |  |  | https://www.notion.so/personal-reflection-template
2025-07-10 | Week 4 | Day 3 | .NET + C# Task | Practice OOP: Class, Object, Inheritance with real-world scenario |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-10 | Week 4 | Day 3 | Angular Task | Components and Modules |  |  | https://angular.io/start
2025-07-10 | Week 4 | Day 3 | Azure Task | Deep dive into App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-10 | Week 4 | Day 3 | Project Module | Design database schema |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-10 | Week 4 | Day 3 | Communication Practice | Explain Angular component to yourself |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-10 | Week 4 | Day 3 | Reflection/Notes | Any blocker faced in setup? |  |  | https://www.notion.so/personal-reflection-template
2025-07-11 | Week 4 | Day 4 | .NET + C# Task | Enhance first Console App |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-11 | Week 4 | Day 4 | Angular Task | Data binding & directives |  |  | https://angular.io/start
2025-07-11 | Week 4 | Day 4 | Azure Task | Deploy sample HTML to App Service |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-11 | Week 4 | Day 4 | Project Module | Enhance login API + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-11 | Week 4 | Day 4 | Communication Practice | Describe Azure in 1 min voice note |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-11 | Week 4 | Day 4 | Reflection/Notes | Comfort level with code so far |  |  | https://www.notion.so/personal-reflection-template
2025-07-12 | Week 4 | Day 5 | .NET + C# Task | Advanced to API: Build simple REST API + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-12 | Week 4 | Day 5 | Angular Task | Routing basics |  |  | https://angular.io/start
2025-07-12 | Week 4 | Day 5 | Azure Task | Install Azure CLI |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-12 | Week 4 | Day 5 | Project Module | Enhance Angular login UI |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-12 | Week 4 | Day 5 | Communication Practice | Mock intro: job interview |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-12 | Week 4 | Day 5 | Reflection/Notes | How did I feel explaining in English? |  |  | https://www.notion.so/personal-reflection-template
2025-07-13 | Week 4 | Day 6 | .NET + C# Task | Entity Framework Core basics |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-13 | Week 4 | Day 6 | Angular Task | Enhance Login form (HTML + CSS) |  |  | https://angular.io/start
2025-07-13 | Week 4 | Day 6 | Azure Task | Learn Azure SQL Basics |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-13 | Week 4 | Day 6 | Project Module | Bind login API to UI + validation |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-13 | Week 4 | Day 6 | Communication Practice | Talk about your project idea |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-13 | Week 4 | Day 6 | Reflection/Notes | What would I improve? |  |  | https://www.notion.so/personal-reflection-template
2025-07-14 | Week 4 | Day 7 | .NET + C# Task | Integrate DB with API (SQL Server) + validation |  |  | https://learn.microsoft.com/en-us/dotnet/csharp/
2025-07-14 | Week 4 | Day 7 | Angular Task | Service and API call integration + validation |  |  | https://angular.io/start
2025-07-14 | Week 4 | Day 7 | Azure Task | Enhance Azure SQL DB |  |  | https://learn.microsoft.com/en-us/training/azure/
2025-07-14 | Week 4 | Day 7 | Project Module | Test end-to-end login flow |  |  | https://docs.github.com/en/get-started/quickstart/create-a-repo
2025-07-14 | Week 4 | Day 7 | Communication Practice | Weekly recap in voice |  |  | https://www.youtube.com/watch?v=Gpj6Qe7pGqg
2025-07-14 | Week 4 | Day 7 | Reflection/Notes | Week 1 wins & learnings |  |  | https://www.notion.so/personal-reflection-template